## Manipur
S. No. | Activity | Year 2016-17 | [7 empty] | Outlay Proposed for 2017-18 | [8 empty] | Outlay Recommended for 2017-18 | [8 empty] | Remarks
|  | Outlay approved by PAB (including spillover) |  | Anticipated Achievement |  |  |  | Savings |  | Deffered Liabilities |  | Spill Over |  | Fresh |  |  | Total |  | Deffered Liabilities |  | Spill Over |  | Fresh |  |  | Total
|  | Phy. | Fin | Phy. | Fin. | Phy. (%) | Fin. (%) | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Unit Cost | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Unit Cost | Phy. | Fin. | Phy. | Fin.
I | ACCESS | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| SSA | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1 | Opening of New Schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1.01 | New Primary School | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 41 | 0 | 41 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
1.02 | Upgradation of PS to UPS | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1.03 | Composite Schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1.04 | Residential schools for specific category of children | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1.05 | Residential Hostel | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
1.06 | Integration of Class V with primary schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
1.07 | Integration of Class VIII with upper primary schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2 | Residential Schools for specific category of children | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Non-recurring (one time grant) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2.01 | Furniture / Equipment (including kitchen equipment) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2.02 | TLM and equipment including library books | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2.03 | Bedding | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2.04 | Replacement of bedding (once in 3 years) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Recurring | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
2.05 | Maintenance @ Rs.1,500/- per child Per month | 9 | 162 | 9 | 162 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 9 | 162 | 9 | 162 | 0 | 0 | 0 | 0 | 18 | 9 | 162 | 9 | 162 | Recommended as proposed
2.06 | Stipend @ Rs.100/- per child per month | 9 | 10.8 | 9 | 10.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | Recommended as proposed
2.07 | Supplementary TLM, Stationery and other educational material @Rs.1,000/- per child per annum | 9 | 9 | 9 | 9 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | Recommended as proposed
2.08 | Salaries | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
(a) | 1 Warden @ Rs.25,000/- per month | 9 | 27 | 9 | 27 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 27 | 9 | 27 | 0 | 0 | 0 | 0 | 3 | 9 | 27 | 9 | 27 | Recommended as proposed
(b) | 4 Fulltime teachers as per RTE Norms @ Rs. 20,000/- per month per teacher | 9 | 86.4 | 9 | 86.4 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 9 | 86.4 | 9 | 86.4 | 0 | 0 | 0 | 0 | 9.6 | 9 | 86.4 | 9 | 86.4 | Recommended as proposed
(c) | 2 Urdu Teachers (only for Blocks with muslim population above 20% and select urban areas) if required @ Rs.12,000/- per month per teacher. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
(d) | 3 Part time teachers @ Rs.5,000/- per month per teacher | 9 | 16.2 | 9 | 16.2 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 9 | 16.2 | 9 | 16.2 | 0 | 0 | 0 | 0 | 1.8 | 9 | 16.2 | 9 | 16.2 | Recommended as proposed
(e) | 1 Full time Accountant @ Rs. 10,000/- per month | 9 | 10.8 | 9 | 10.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | Recommended as proposed
(f) | 2 Support staff - (Accountant/Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | 9 | 10.8 | 9 | 10.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | 0 | 0 | 0 | 0 | 1.2 | 9 | 10.8 | 9 | 10.8 | Recommended as proposed
(g) | 1 Head Cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | 9 | 16.2 | 9 | 16.2 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 9 | 16.2 | 9 | 16.2 | 0 | 0 | 0 | 0 | 1.8 | 9 | 16.2 | 9 | 16.2 | Recommended as proposed
2.09 | Specific Skill training @ Rs.1,000/- per child per annum | 9 | 9 | 9 | 9 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | Recommended as proposed
2.1 | Electricity / water charges @ Rs. 1,000/- per child per annum | 9 | 9 | 9 | 9 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 1 | 9 | 9 | 9 | 9 | Recommended as proposed
2.11 | Medical care/contingencies @ Rs.1,250/- per child per annum | 9 | 11.25 | 9 | 11.25 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 9 | 11.25 | 9 | 11.25 | 0 | 0 | 0 | 0 | 1.25 | 9 | 11.25 | 9 | 11.25 | Recommended as proposed
2.12 | Maintenance @ Rs. 750/- per child per annum | 9 | 6.75 | 9 | 6.75 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 9 | 6.75 | 9 | 6.75 | 0 | 0 | 0 | 0 | 0.75 | 9 | 6.75 | 9 | 6.75 | Recommended as proposed
2.13 | Miscellaneous @ Rs. 750/- per child per annum | 9 | 6.75 | 9 | 6.75 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 9 | 6.75 | 9 | 6.75 | 0 | 0 | 0 | 0 | 0.75 | 9 | 6.75 | 9 | 6.75 | Recommended as proposed
2.14 | Preparatory camps @ Rs. 300/- per child per annum | 9 | 1.8 | 9 | 1.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | Recommended as proposed
2.15 | P.T.A / school functions @ Rs. 300/- per child per annum | 9 | 1.8 | 9 | 1.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | Recommended as proposed
2.16 | Provision of Rent @ Rs. 10,000/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 9 | 27 | 9 | 27 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
2.17 | Capacity Building @ Rs. 500/- per child per annum | 9 | 4.5 | 9 | 4.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 9 | 4.5 | 9 | 4.5 | 0 | 0 | 0 | 0 | 0.5 | 9 | 4.5 | 9 | 4.5 | Recommended as proposed
2.18 | Physical / Self Defence Training @ Rs.200/- per child per annum | 9 | 1.8 | 9 | 1.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | 0 | 0 | 0 | 0 | 0.2 | 9 | 1.8 | 9 | 1.8 | Recommended as proposed
| Sub Total (Recurring) | 9 | 401.85 | 9 | 401.85 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 428.85 | 9 | 428.85 | 0 | 0 | 0 | 0 |  | 9 | 401.85 | 9 | 401.85
| Total (Non Recurring + Recurring) | 9 | 401.85 | 9 | 401.85 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 437.85 | 9 | 437.85 | 0 | 0 | 0 | 0 |  | 9 | 401.85 | 9 | 401.85
3 | Residential Hostel for specific category of children | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Non-recurring (one time grant) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
3.01 | Furniture/ Equipment (including kitchen) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 54 | 18 | 54 | 0 | 0 | 0 | 0 | 3 | 7 | 21 | 7 | 21
3.02 | TLM and equipment including library books | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 18 | 63 | 18 | 63 | 0 | 0 | 0 | 0 | 3.5 | 7 | 24.5 | 7 | 24.5
3.03 | Bedding (new) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 18 | 13.5 | 18 | 13.5 | 0 | 0 | 0 | 0 | 0.75 | 7 | 5.25 | 7 | 5.25
3.04 | Replacement of bedding (once in 3 years) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total (Non Recurring) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 130.5 | 18 | 130.5 | 0 | 0 | 0 | 0 |  | 7 | 50.75 | 7 | 50.75
| Recurring | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
3.05 | Maintenance @ Rs.1,500/- per child per month | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 324 | 18 | 324 | 0 | 0 | 0 | 0 | 18 | 7 | 126 | 7 | 126
3.06 | Stipend @ Rs.100/- per child per month | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 18 | 21.6 | 18 | 21.6 | 0 | 0 | 0 | 0 | 1.2 | 7 | 8.4 | 7 | 8.4
3.07 | Supplementary TLM, Stationery and other educational material @Rs.1,000/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 7 | 7 | 7 | 7
3.08 | Salaries | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0
(a) | 1 Warden @ Rs. 25,000/- per month | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 54 | 18 | 54 | 0 | 0 | 0 | 0 | 3 | 7 | 21 | 7 | 21
(b) | 4 Fulltime teachers as per RTE Norms @ Rs. 20,000/- per month per teacher | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 18 | 172.8 | 18 | 172.8 | 0 | 0 | 0 | 0 | 9.6 | 7 | 67.2 | 7 | 67.2
(c) | 2 Urdu Teachers (only for Blocks with muslim population above 20% and select urban areas) if required @ Rs.12,000/- per month per teacher. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
(d) | 3 Part time teachers @ Rs.5,000/- per month per teacher | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 18 | 32.4 | 18 | 32.4 | 0 | 0 | 0 | 0 | 1.8 | 7 | 12.6 | 7 | 12.6
(e) | 1 Full time Accountant @ Rs. 10,000/- per month | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 18 | 21.6 | 18 | 21.6 | 0 | 0 | 0 | 0 | 1.2 | 7 | 8.4 | 7 | 8.4
(f) | 2 Support staff - (Accountant/Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 18 | 21.6 | 18 | 21.6 | 0 | 0 | 0 | 0 | 1.2 | 7 | 8.4 | 7 | 8.4
(g) | 1 Head Cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 18 | 32.4 | 18 | 32.4 | 0 | 0 | 0 | 0 | 1.8 | 7 | 12.6 | 7 | 12.6
3.09 | Specific Skill training @ Rs.1000/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 7 | 7 | 7 | 7
3.1 | Electricity / water charges @ Rs. 1,000/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 1 | 7 | 7 | 7 | 7
3.11 | Medical care/contingencies @ Rs.1,250/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 18 | 22.5 | 18 | 22.5 | 0 | 0 | 0 | 0 | 1.25 | 7 | 8.75 | 7 | 8.75
3.12 | Maintenance @ Rs. 750/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 18 | 13.5 | 18 | 13.5 | 0 | 0 | 0 | 0 | 0.75 | 7 | 5.25 | 7 | 5.25
3.13 | Miscellaneous @ Rs. 750/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 18 | 13.5 | 18 | 13.5 | 0 | 0 | 0 | 0 | 0.75 | 7 | 5.25 | 7 | 5.25
3.14 | Preparatory camps @ Rs. 300/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 18 | 5.4 | 18 | 5.4 | 0 | 0 | 0 | 0 | 0.3 | 7 | 2.1 | 7 | 2.1
3.15 | P.T.A / school functions @ Rs. 300/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 18 | 5.4 | 18 | 5.4 | 0 | 0 | 0 | 0 | 0.3 | 7 | 2.1 | 7 | 2.1
3.16 | Provision of Rent @ Rs. 10,000/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 180 | 18 | 180 | 0 | 0 | 0 | 0 | 10 | 7 | 70 | 7 | 70
3.17 | Capacity Building @ Rs. 500/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 18 | 9 | 18 | 9 | 0 | 0 | 0 | 0 | 0.5 | 7 | 3.5 | 7 | 3.5
3.18 | Physical / Self Defence Training @ Rs.200/- per child per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 18 | 3.6 | 18 | 3.6 | 0 | 0 | 0 | 0 | 0.2 | 7 | 1.4 | 7 | 1.4
| Sub Total (Recurring) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 987.3 | 18 | 987.3 | 0 | 0 | 0 | 0 |  | 7 | 383.95 | 7 | 383.95
| Total (Non Recurring + Recurring) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 1117.8 | 18 | 1117.8 | 0 | 0 | 0 | 0 |  | 7 | 434.7 | 7 | 434.7
4 | Transport/Escort Facility | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
4.01 | Children in remote habitation | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
4.02 | Urban deprived children/children without adult protection | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
5 | Reimbursement of Fee against 25% admission under Section 12(1)(c) of RTE Act 2009 (Entry Level) subject to upper limit of 20% of AWP&B guidelines issued by MHRD | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Special Training for mainstreaming of out of school children | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
6.01 | Residential (Fresh) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 2102 | 420.4 | 2102 | 376.84 | 100% | 89.64% | 0 | 43.56 | 0 | 0 | 0 | 0 | 0.2 | 1476 | 295.2 | 1476 | 295.2 | 0 | 0 | 0 | 0 | 0.2 | 1476 | 295.2 | 1476 | 295.2 | Recommended as proposed
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 2102 | 420.4 | 2102 | 376.84 | 100% | 89.64% | 0 | 43.56 | 0 | 0 | 0 | 0 |  | 1476 | 295.2 | 1476 | 295.2 | 0 | 0 | 0 | 0 |  | 1476 | 295.2 | 1476 | 295.2
6.02 | Residential (Continuing from previous year) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 2238 | 447.6 | 2238 | 401.23 | 100% | 89.64% | 0 | 46.37 | 0 | 0 | 0 | 0 | 0.2 | 1594 | 318.8 | 1594 | 318.8 | 0 | 0 | 0 | 0 | 0.2 | 1594 | 318.8 | 1594 | 318.8 | Recommended as proposed
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 2238 | 447.6 | 2238 | 401.23 | 100% | 89.64% | 0 | 46.37 | 0 | 0 | 0 | 0 |  | 1594 | 318.8 | 1594 | 318.8 | 0 | 0 | 0 | 0 |  | 1594 | 318.8 | 1594 | 318.8
6.03 | Non-Residential (Fresh) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 3215 | 192.9 | 3215 | 172.92 | 100% | 89.64% | 0 | 19.98 | 0 | 0 | 0 | 0 | 0.06 | 521 | 31.26 | 521 | 31.26 | 0 | 0 | 0 | 0 | 0.06 | 521 | 31.26 | 521 | 31.26 | Recommended as proposed
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 3215 | 192.9 | 3215 | 172.92 | 100% | 89.64% | 0 | 19.98 | 0 | 0 | 0 | 0 |  | 521 | 31.26 | 521 | 31.26 | 0 | 0 | 0 | 0 |  | 521 | 31.26 | 521 | 31.26
6.04 | Non-Residential (Continuing from previous year) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 2892 | 173.52 | 2892 | 155.55 | 100% | 89.64% | 0 | 17.97 | 0 | 0 | 0 | 0 | 0.06 | 2404 | 144.24 | 2404 | 144.24 | 0 | 0 | 0 | 0 | 0.06 | 2404 | 144.24 | 2404 | 144.24 | Recommended as proposed
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 2892 | 173.52 | 2892 | 155.55 | 100% | 89.64% | 0 | 17.97 | 0 | 0 | 0 | 0 |  | 2404 | 144.24 | 2404 | 144.24 | 0 | 0 | 0 | 0 |  | 2404 | 144.24 | 2404 | 144.24
6.05 | Madrasa/ Maktav | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
6.06 | Seasonal Hostel | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 12 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (b) 9 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) 6 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) 3 months | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 10447 | 1234.42 | 10447 | 1106.54 | 100% | 89.64% | 0 | 127.88 | 0 | 0 | 0 | 0 |  | 5995 | 789.5 | 5995 | 789.5 | 0 | 0 | 0 | 0 |  | 5995 | 789.5 | 5995 | 789.5
| Total (Access) | 10447 | 1234.42 | 10447 | 1106.54 | 100% | 89.64% | 0 | 127.88 | 0 | 0 | 0 | 0 | 0 | 5995 | 789.5 | 5995 | 789.5 | 0 | 0 | 0 | 0 | 0 | 5995 | 789.5 | 5995 | 789.5
II | RETENTION | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
7 | Free Text Book | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
7.01 | Free Text Book (P) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 86748 | 130.122 | 86748 | 130.122 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.0015 | 78633 | 117.9495 | 78633 | 117.9495 | 0 | 0 | 0 | 0 | 0.0015 | 78633 | 117.9495 | 78633 | 117.9495 | Recommended as proposed
| (b) Braille Books Class I & II | 40 | 0.06 | 40 | 0.06 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.0015 | 40 | 0.06 | 40 | 0.06 | 0 | 0 | 0 | 0 | 0.0015 | 40 | 0.06 | 40 | 0.06 | Recommended as proposed
| (c) Large Print Books Class I & II | 203 | 0.3045 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0.0015 | 203 | 0.3045 | 203 | 0.3045 | 0 | 0 | 0 | 0 | 0.0015 | 203 | 0.3045 | 203 | 0.3045 | Recommended as proposed
| (d) Class III to V | 82314 | 123.471 | 82314 | 123.471 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.0015 | 67062 | 100.593 | 67062 | 100.593 | 0 | 0 | 0 | 0 | 0.0015 | 67062 | 100.593 | 67062 | 100.593 | Recommended as proposed
| (e) Braille Books Class III to V | 95 | 0.1425 | 95 | 0.1425 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.0015 | 95 | 0.1425 | 95 | 0.1425 | 0 | 0 | 0 | 0 | 0.0015 | 95 | 0.1425 | 95 | 0.1425 | Recommended as proposed
| (f) Large Print Books Class III to V | 590 | 0.885 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0.0015 | 590 | 0.885 | 590 | 0.885 | 0 | 0 | 0 | 0 | 0.0015 | 590 | 0.885 | 590 | 0.885 | Recommended as proposed | 0
7.02 | Free Text Book (UP) | 49613 | 124.0325 | 44986 | 112.47 | 90.67% | 90.68% | 4627 | 11.5625 | 0 | 0 | 0 | 0 | 0.0025 | 41564 | 103.91 | 41564 | 103.91 | 0 | 0 | 0 | 0 | 0.0025 | 41564 | 103.91 | 41564 | 103.91 | Recommended as proposed | 0
7.03 | Braille Books (UP) | 62 | 0.155 | 62 | 0.155 | 100% | 100% | 0 | 0 | 0 | 0 | 0 |  | 0.0025 | 62 | 0.155 | 62 | 0.155 | 0 | 0 | 0 | 0 | 0.0025 | 62 | 0.155 | 62 | 0.155 | Recommended as proposed | 0
7.04 | Large Print Books (UP) | 455 | 1.1375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0025 | 455 | 1.1375 | 455 | 1.1375 | 0 | 0 | 0 | 0 | 0.0025 | 455 | 1.1375 | 455 | 1.1375 | Recommended as proposed
| Sub Total | 220120 | 380.31 | 215493 | 368.7475 | 97.9% | 96.96% | 4627 | 11.5625 | 0 | 0 | 0 | 0 |  | 188704 | 325.137 | 188704 | 325.137 | 0 | 0 | 0 | 0 |  | 188704 | 325.137 | 188704 | 325.137
8 | Provision of 2 sets of Uniform | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
8.01 | All Girls | 95640 | 382.56 | 95640 | 382.56 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 80121 | 320.484 | 80121 | 320.484 | 0 | 0 | 0 | 0 | 0.004 | 80121 | 320.484 | 80121 | 320.484 | Recommended as proposed
8.02 | SC Boys | 4003 | 16.012 | 4003 | 16.012 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 2961 | 11.844 | 2961 | 11.844 | 0 | 0 | 0 | 0 | 0.004 | 2961 | 11.844 | 2961 | 11.844
8.03 | ST Boys | 50121 | 200.484 | 50121 | 200.484 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 42765 | 171.06 | 42765 | 171.06 | 0 | 0 | 0 | 0 | 0.004 | 42765 | 171.06 | 42765 | 171.06
8.04 | BPL Boys | 36675 | 146.7 | 36675 | 146.7 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.004 | 31888 | 127.552 | 31888 | 127.552 | 0 | 0 | 0 | 0 | 0.004 | 31888 | 127.552 | 31888 | 127.552
| Sub Total | 186439 | 745.756 | 186439 | 745.756 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 157735 | 630.94 | 157735 | 630.94 | 0 | 0 | 0 | 0 |  | 157735 | 630.94 | 157735 | 630.94
9 | Teaching Learning Equipment (TLE) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
9.01 | New Primary | 60 | 12 | 60 | 12 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 116 | 23.2 | 116 | 23.2 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | Not recommended
9.02 | New Upper Primary | 5 | 2.5 | 5 | 2.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 29 | 14.5 | 29 | 14.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
9.03 | Integration of Class V | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 65 | 14.5 | 65 | 14.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 145 | 37.7 | 145 | 37.7 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total ( Retention) | 406624 | 1140.566 | 401997 | 1129.0035 | 98.86% | 98.99% | 4627 | 11.5625 | 0 | 0 | 0 | 0 |  | 346584 | 993.777 | 346584 | 993.777 | 0 | 0 | 0 | 0 |  | 346439 | 956.077 | 346439 | 956.077
III | ENHANCING QUALITY | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10 | New Teachers Salary | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.01 | New Primary Teachers (Regular) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.02 | New Primary Teachers (Contractual) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.03 | Head Teachers for Primary (if the number of children exceeds 150 in a school) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.04 | Subject specific New Upper Primary Teachers (Regular) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Science and Mathematics | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.351 | 364 | 1533.168 | 364 | 1533.168 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
| (b) Social Studies | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) Languages | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.05 | Subject specific New Upper Primary Teachers (Contractual) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Science and Mathematics | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (b) Social Studies | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) Languages | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 364 | 1533.168 | 364 | 1533.168 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.06 | Head Teacher for Upper Primary (if the number of children exceeds 100 in a school) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.07 | Part Time Instructors (if the number of children exceeds 100 in a school) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Art Education | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (b) Health and Physical Education | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) Work Education | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 364 | 1533.168 | 364 | 1533.168 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Teachers' Salary (Recurring-sanctioned earlier) in position | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Primary teachers | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.08 | Primary Teachers - Existing, in position (Regular) | 1919 | 7366.6572 | 1919 | 4354.878 | 100% | 59.12% | 1919 | 3011.7792 | 0 | 0 | 1919 | 3011.7792 | 0.3299 | 1919 | 7596.9372 | 1919 | 10608.7164 | 0 | 0 | 1919 | 3011.7792 | 0.3199 | 1919 | 7596.9372 | 3838 | 10608.7164
10.09 | Primary Teachers - Existing, in position (Contractual) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.1 | Head Teacher for Primary | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.11 | Additional Teachers - PS (Regular) | 378 | 1451.0664 | 378 | 857.8164 | 100% | 59.12% | 378 | 593.25 | 0 | 0 | 378 | 593.25 | 0.3299 | 378 | 1496.4264 | 378 | 2089.6764 | 0 | 0 | 378 | 593.25 | 0.3199 | 378 | 1496.4264 | 756 | 2089.6764
| Upper Primary teachers | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.12 | UP Teachers (Regular)-Existing | 100 | 410.04 | 100 | 242.396 | 100% | 59.12% | 100 | 167.644 | 0 | 0 | 100 | 167.644 | 0.3517 | 100 | 422.04 | 100 | 589.684 | 0 | 0 | 100 | 167.644 | 0.3417 | 100 | 422.04 | 200 | 589.684
10.13 | Subject specific Upper Primary Teachers (Regular) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Science and Mathematics | 158 | 647.8632 | 158 | 382.9924 | 100% | 59.12% | 158 | 264.8708 | 0 | 0 | 158 | 264.8708 | 0.3517 | 158 | 666.8232 | 158 | 931.694 | 0 | 0 | 158 | 264.8708 | 0.3417 | 158 | 666.8232 | 316 | 931.694
| (b) Social Studies | 158 | 647.8632 | 158 | 382.9924 | 100% | 59.12% | 158 | 264.8708 | 0 | 0 | 158 | 264.8708 | 0.3517 | 158 | 666.8232 | 158 | 931.694 | 0 | 0 | 158 | 264.8708 | 0.3417 | 158 | 666.8232 | 316 | 931.694
| (c) Languages | 158 | 647.8632 | 158 | 382.9924 | 100% | 59.12% | 158 | 264.8708 | 0 | 0 | 158 | 264.8708 | 0.3517 | 158 | 666.8232 | 158 | 931.694 | 0 | 0 | 158 | 264.8708 | 0.3417 | 158 | 666.8232 | 316 | 931.694
10.14 | Subject specific Upper Primary Teachers (Contract) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Science and Mathematics | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (b) Social Studies | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) Languages | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.15 | Head Teachers for Upper Primary in position (if the number of children exceeds 100 in a school) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10.16 | Part Time Instructors | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Art Education | 106 | 228.96 | 0 | 0 |  |  | 106 | 228.96 | 0 | 0 | 106 | 228.96 | 0.195 | 106 | 248.04 | 106 | 477 | 0 | 0 | 106 | 228.96 | 0.18 | 106 | 248.04 | 212 | 477
| (b) Health and Physical Education | 106 | 228.96 | 0 | 0 |  |  | 106 | 228.96 | 0 | 0 | 106 | 228.96 | 0.195 | 106 | 248.04 | 106 | 477 | 0 | 0 | 106 | 228.96 | 0.18 | 106 | 248.04 | 212 | 477
| (c) Work Education | 106 | 228.96 | 0 | 0 |  |  | 106 | 228.96 | 0 | 0 | 106 | 228.96 | 0.195 | 106 | 248.04 | 106 | 477 | 0 | 0 | 106 | 228.96 | 0.18 | 106 | 248.04 | 212 | 477
| Sub Total | 3189 | 11858.2332 | 2871 | 6604.0676 | 90.03% | 55.69% | 3189 | 5254.1656 | 0 | 0 | 3189 | 5254.1656 |  | 3189 | 12259.9932 | 3189 | 17514.1588 | 0 | 0 | 3189 | 5254.1656 |  | 3189 | 12259.9932 | 6378 | 17514.1588
| Total (New+Recurring) | 3189 | 11858.2332 | 2871 | 6604.0676 | 90.03% | 55.69% | 3189 | 5254.1656 | 0 | 0 | 3189 | 5254.1656 |  | 3553 | 13793.1612 | 3553 | 19047.3268 | 0 | 0 | 3189 | 5254.1656 |  | 3189 | 12259.9932 | 6378 | 17514.1588
11 | Training | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Teachers | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11.01 | Refresher In-service Teachers' Training at BRC level | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 5835 | 29.175 | 5835 | 29.175 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 5835 | 116.7 | 5835 | 116.7 | 0 | 0 | 0 | 0 | 0.01 | 5835 | 58.35 | 5835 | 58.35 | Recommended as appraised
| (b) Class III to V | 8752 | 43.76 | 8752 | 43.76 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 8752 | 175.04 | 8752 | 175.04 | 0 | 0 | 0 | 0 | 0.01 | 8752 | 87.52 | 8752 | 87.52
| (c) Class VI to VIII | 3880 | 19.4 | 3880 | 19.4 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 3880 | 77.6 | 3880 | 77.6 | 0 | 0 | 0 | 0 | 0.01 | 3880 | 38.8 | 3880 | 38.8
11.02 | One day monthly cluster level meetings for 10 months for all teachers at CRC level -5 days | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11.03 | Follow up meetings at CRC level | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 5835 | 29.175 | 5835 | 29.175 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 5835 | 58.35 | 5835 | 58.35 | 0 | 0 | 0 | 0 | 0.005 | 5835 | 58.35 | 5835 | 58.35 | Recommended as proposed
| (b) Class III to V | 8752 | 43.76 | 8752 | 43.76 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 8752 | 87.52 | 8752 | 87.52 | 0 | 0 | 0 | 0 | 0.005 | 8752 | 87.52 | 8752 | 87.52
| (c) Class VI to VIII | 3880 | 19.4 | 3880 | 19.4 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 3880 | 38.8 | 3880 | 38.8 | 0 | 0 | 0 | 0 | 0.005 | 3880 | 38.8 | 3880 | 38.8
11.04 | Induction Training for Newly Recruited Teachers- 30 days | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.06 | 710 | 42.6 | 710 | 42.6 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
11.05 | Training of untrained Teachers | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Trainng of untrained teachers to acquire professional qualifications over a two year period (Year I) | 1659 | 99.54 |  |  |  |  | 1659 | 99.54 | 0 | 0 | 0 | 0 | 0.06 | 1659 | 99.54 | 1659 | 99.54 | 0 | 0 | 0 | 0 | 0.06 | 1659 | 99.54 | 1659 | 99.54 | Recommended as proposed
| (b) Trainng of untrained teachers to acquire professional qualifications over a two year period (Year II) | 2224 | 133.44 |  |  |  |  | 2224 | 133.44 | 0 | 0 | 0 | 0 | 0.12 | 2224 | 266.88 | 2224 | 266.88 | 0 | 0 | 0 | 0 | 0.06 | 2224 | 266.88 | 2224 | 266.88 | Recommended as proposed
| (B) Training of Resource Persons | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11.06 | Training for Resource Persons & Master Trainers (this may include BRCCs,BRPs, CRCCs, DIET faculties and any other persons designated as Resource Persons) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 100 | 0.5 | 100 | 0.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 100 | 2 | 100 | 2 | 0 | 0 | 0 | 0 | 0.005 | 100 | 2 | 100 | 2 | Recommended as proposed
| (b) Class III to V | 100 | 0.5 | 100 | 0.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 100 | 2 | 100 | 2 | 0 | 0 | 0 | 0 | 0.005 | 100 | 2 | 100 | 2
| (c) Class VI to VIII | 150 | 0.75 | 150 | 0.75 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 150 | 3 | 150 | 3 | 0 | 0 | 0 | 0 | 0.005 | 150 | 3 | 150 | 3
| (C) NUEPA School Leadership Programme | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11.07 | RPs Training | 15 | 0.3 | 0 | 0 |  |  | 15 | 0.3 | 0 | 0 | 0 | 0 | 0.02 | 15 | 0.3 | 15 | 0.3 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 | 0 | 0 | Not recommended
11.08 | Head Teacher Training | 500 | 8 | 0 | 0 |  |  | 500 | 8 | 0 | 0 | 0 | 0 | 0.016 | 500 | 8 | 500 | 8 | 0 | 0 | 0 | 0 | 0.016 | 900 | 14.4 | 900 | 14.4
11.09 | Training of Head Master on NUEPA Moduel (16 days) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11.1 | Resource person for Head Teacher Training (10 days) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 41682 | 427.7 | 37284 | 186.42 | 89.45% | 43.59% | 4398 | 241.28 | 0 | 0 | 0 | 0 |  | 42392 | 978.33 | 42392 | 978.33 | 0 | 0 | 0 | 0 |  | 42067 | 757.16 | 42067 | 757.16
12 | Academic Support through Block Resource Centre/ URC | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
12.01 | Salary of Faculty and Staff | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) 6 RPs at BRC for subject specific training | 137 | 389.628 | 137 | 389.628 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.325 | 210 | 819 | 210 | 819 | 0 | 0 | 0 | 0 | 0.3492 | 137 | 574.0848 | 137 | 574.0848 | Recommended as appraised
| (b) 2 RPs for CWSN | 66 | 118.8 | 66 | 118.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.321 | 70 | 269.64 | 70 | 269.64 | 0 | 0 | 0 | 0 | 0.3492 | 66 | 276.5664 | 66 | 276.5664
| (c) 1 MIS Coordinator | 28 | 79.632 | 28 | 79.632 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.325 | 35 | 136.5 | 35 | 136.5 | 0 | 0 | 0 | 0 | 0.3518 | 28 | 118.2048 | 28 | 118.2048
| (d) 1 Datra Entry Operator | 23 | 41.4 | 23 | 41.4 | 100% | 100% | 0 | 0 | 0 |  | 0 | 0 | 0.198 | 35 | 83.16 | 35 | 83.16 | 0 | 0 | 0 | 0 | 0.192 | 23 | 52.992 | 23 | 52.992
| (e) 1 Accountant-cum-support staff for every 50 schools | 47 | 84.6 | 47 | 84.6 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.198 | 65 | 154.44 | 65 | 154.44 | 0 | 0 | 0 | 0 | 0.204 | 47 | 115.056 | 47 | 115.056
12.02 | Furniture Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
12.03 | Replacement of furniture (Once in 5 years) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
12.04 | Contingency Grant | 35 | 17.5 | 35 | 17.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 35 | 17.5 | 35 | 17.5 | 0 | 0 | 0 | 0 | 0.5 | 35 | 17.5 | 35 | 17.5 | Recommended as proposed
12.05 | Meeting TA (@ Rs. 2500 P.M.) | 35 | 10.5 | 35 | 10.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 35 | 10.5 | 35 | 10.5 | 0 | 0 | 0 | 0 | 0.3 | 35 | 10.5 | 35 | 10.5
12.06 | TLM Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 35 | 3.5 | 35 | 3.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
12.07 | Maintenance Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 35 | 3.5 | 35 | 3.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 371 | 742.06 | 371 | 742.06 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 555 | 1497.74 | 555 | 1497.74 | 0 | 0 | 0 | 0 |  | 371 | 1164.904 | 371 | 1164.904
13 | Academic Support through Cluster Resource Centres | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
13.01 | Salary of Cluster Coordinator, full time and in position | 146 | 415.224 | 146 | 242.22 | 100% | 58.33% | 0 | 173.004 | 0 | 0 | 0 | 0 | 0.325 | 225 | 877.02 | 225 | 877.02 | 0 | 0 | 0 | 0 | 0.3492 | 146 | 611.7984 | 146 | 611.7984 | Recommended as appraised
13.02 | Furniture Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
13.03 | Replacement of Funiture Grant (Once in 5 years) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
13.04 | Contingency Grant | 225 | 22.5 | 225 | 22.5 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 225 | 22.5 | 225 | 22.5 | 0 | 0 | 0 | 0 | 0.1 | 225 | 22.5 | 225 | 22.5 | Recommended as proposed
13.05 | Meeting TA | 225 | 27 | 225 | 27 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.12 | 225 | 27 | 225 | 27 | 0 | 0 | 0 | 0 | 0.12 | 225 | 27 | 225 | 27
13.06 | TLM Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 225 | 6.75 | 225 | 6.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
13.07 | Maintenace Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 225 | 4.5 | 225 | 4.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 596 | 464.724 | 596 | 291.72 | 100% | 62.77% | 0 | 173.004 | 0 | 0 | 0 | 0 |  | 1125 | 937.77 | 1125 | 937.77 | 0 | 0 | 0 | 0 |  | 596 | 661.2984 | 596 | 661.2984
14 | Computer Aided Education in UPS under Innovation | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
14.01 | Computer Aided Education in Upper Primary Schools (Physical target = No. of schools per district) | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (a) Number of districts | 9 | 225 | 9 | 115.47 | 100% | 51.32% | 0 | 109.53 | 0 | 0 | 0 | 0 | 50 | 9 | 450 | 9 | 450 | 0 | 0 | 0 | 0 | 50 | 9 | 450 | 9 | 450 | Recommended as proposed
| (b) Number of schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 9 | 225 | 9 | 115.47 | 100% | 51.32% | 0 | 109.53 | 0 | 0 | 0 | 0 |  | 9 | 450 | 9 | 450 | 0 | 0 | 0 | 0 |  | 9 | 450 | 9 | 450
15 | Libraries in Schools | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
15.01 | Primary | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 2859 | 85.77 | 2859 | 85.77 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
15.02 | Upper Primary | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 695 | 69.5 | 695 | 69.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 3554 | 155.27 | 3554 | 155.27 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Total ( Quality Interventions) | 45847 | 13717.7172 | 41131 | 7939.7376 | 89.71% | 57.88% | 7587 | 5777.9796 | 0 | 0 | 3189 | 5254.1656 |  | 51188 | 17812.2712 | 51188 | 23066.4368 | 0 | 0 | 3189 | 5254.1656 |  | 46232 | 15293.3556 | 49421 | 20547.5212
IV | ANNUAL GRANTS | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
16 | Teachers' Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
16.01 | Primary | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 5263 | 26.315 | 5263 | 26.315 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 5263 | 26.315 | 5263 | 26.315 | 0 | 0 | 0 | 0 | 0.005 | 5263 | 26.315 | 5263 | 26.315 | Recommended as proposed
| (b) Class III to V | 7894 | 39.47 | 7894 | 39.47 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 7894 | 39.47 | 7894 | 39.47 | 0 | 0 | 0 | 0 | 0.005 | 7894 | 39.47 | 7894 | 39.47
16.02 | Upper Primary: Class VI to VIII | 3155 | 15.775 | 3155 | 15.775 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 3155 | 15.775 | 3155 | 15.775 | 0 | 0 | 0 | 0 | 0.005 | 3155 | 15.775 | 3155 | 15.775
| Sub Total | 16312 | 81.56 | 16312 | 81.56 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 16312 | 81.56 | 16312 | 81.56 | 0 | 0 | 0 | 0 |  | 16312 | 81.56 | 16312 | 81.56
17 | School Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
17.01 | Primary | 3162 | 158.1 | 3162 | 158.1 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 3647 | 182.35 | 3647 | 182.35 | 0 | 0 | 0 | 0 | 0.05 | 3647 | 182.35 | 3647 | 182.35 | Recommended as proposed
17.02 | Upper Primary | 851 | 59.57 | 851 | 59.57 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.07 | 1022 | 71.54 | 1022 | 71.54 | 0 | 0 | 0 | 0 | 0.07 | 1022 | 71.54 | 1022 | 71.54
| Sub Total | 4013 | 217.67 | 4013 | 217.67 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 4669 | 253.89 | 4669 | 253.89 | 0 | 0 | 0 | 0 |  | 4669 | 253.89 | 4669 | 253.89
18 | Research, Evaluation, Monitoring & Supervision | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
18.01 | REMS activities | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.0145 | 4669 | 67.7005 | 4669 | 67.7005 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
18.02 | Monitoring & Supervision | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 4669 | 67.7005 | 4669 | 67.7005 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
19 | Maintenance Grant | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
19.01 | Maintenance Grant ( PS & UPS) | 3302 | 245.95 | 3302 | 245.95 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 3253 | 242.73 | 3253 | 242.73 | 0 | 0 | 0 | 0 |  | 3253 | 242.73 | 3253 | 242.73 | Recommended as proposed
| Sub Total | 3302 | 245.95 | 3302 | 245.95 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 3253 | 242.73 | 3253 | 242.73 | 0 | 0 | 0 | 0 |  | 3253 | 242.73 | 3253 | 242.73
| Total (Annual Grants) | 23627 | 545.18 | 23627 | 545.18 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 28903 | 645.8805 | 28903 | 645.8805 | 0 | 0 | 0 | 0 |  | 24234 | 578.18 | 24234 | 578.18
V | BRIDGING GENDER AND SOCIAL CATEGORY GAPS | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
20 | Interventions for CWSN | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
20.01 | Provision for Inclusive Education | 6514 | 195.42 | 6514 | 195.42 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.03 | 5802 | 174.06 | 5802 | 174.06 | 0 | 0 | 0 | 0 | 0.03 | 5737 | 172.11 | 5737 | 172.11 | Recommended as appraised
| Sub Total | 6514 | 195.42 | 6514 | 195.42 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 5802 | 174.06 | 5802 | 174.06 | 0 | 0 | 0 | 0 |  | 5737 | 172.11 | 5737 | 172.11
21 | Innovation Head up to Rs. 50 lakh per district | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | Funds are proposed for PBBB & Lamjing Maheikol |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
21.01 | Girls Education | 9 | 112.5 | 9 | 23.5 | 100% | 20.89% | 0 | 89 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5
21.02 | Intervention for SC / ST children | 9 | 112.5 | 9 | 22.5 | 100% | 20% | 0 | 90 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5
21.03 | Intervention for Minority Community children | 9 | 112.5 | 9 | 22.5 | 100% | 20% | 0 | 90 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5
21.04 | Intervention for Urban Deprived children | 9 | 112.5 | 9 | 22.5 | 100% | 20% | 0 | 90 | 0 | 0 | 0 |  | 12.5 | 9 | 112.5 | 9 | 112.5 | 0 | 0 | 0 | 0 | 12.5 | 9 | 112.5 | 9 | 112.5
| Sub Total | 36 | 450 | 36 | 91 | 100% | 20.22% | 0 | 359 | 0 | 0 | 0 | 0 | 50 | 36 | 450 | 36 | 450 | 0 | 0 | 0 | 0 | 0 | 36 | 450 | 36 | 450
22 | SMC/PRI Training | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
22.01 | Residential (3 days) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.006 | 16572 | 99.432 | 16572 | 99.432 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
22.02 | Non-residential (3 days) | 19848 | 59.544 | 19848 | 59.544 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.003 | 19638 | 58.914 | 19638 | 58.914 | 0 | 0 | 0 | 0 | 0.003 | 19608 | 58.824 | 19608 | 58.824 | Recommended as appraised
| Sub Total | 19848 | 59.544 | 19848 | 59.544 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 36210 | 158.346 | 36210 | 158.346 | 0 | 0 | 0 | 0 |  | 19608 | 58.824 | 19608 | 58.824
| Total Gender | 26398 | 704.964 | 26398 | 345.964 | 100% | 49.08% | 0 | 359 | 0 | 0 | 0 | 0 |  | 42048 | 782.406 | 42048 | 782.406 | 0 | 0 | 0 | 0 |  | 25381 | 680.934 | 25381 | 680.934
VI | SCHOOL INFRASTRUCTURE | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23 | Civil Works Construction | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.01 | New Primary School (Rural) | 269 | 1651.2273 | 83 | 624.87 | 30.86% | 37.84% | 186 | 1026.3573 | 0 | 0 | 186 | 1026.3573 | 29.652 | 90 | 2642.4 | 280 | 3668.7573 | 0 | 0 | 186 | 1026.3573 | 29.36 | 71 | 2084.56 | 257 | 3110.9173 | 71 primary schools approved @29.36
23.02 | New Primary School (Urban) | 117 | 1165.3856 | 33 | 407.99 | 28.21% | 35.01% | 84 | 757.3956 | 0 | 0 | 84 | 757.3956 | 40.122 | 53 | 2119.099 | 137 | 2876.4946 | 0 | 0 | 84 | 757.3956 | 39.983 | 17 | 679.711 | 101 | 1437.1066 | 17 primary schools approved @39.983
23.03 | New Upper Primary (Rural) | 136 | 1875.88 | 26 | 566.13 | 19.12% | 30.18% | 110 | 1309.75 | 0 | 0 | 110 | 1309.75 | 34.636 | 32 | 1112.896 | 142 | 2422.646 | 0 | 0 | 110 | 1309.75 | 9.935 | 3 | 29.805 | 113 | 1339.555 | 3 classroom approved @9.9350
23.04 | New Upper Primary (Urban) | 8 | 87.495 | 3 | 9.85 | 37.5% | 11.26% | 5 | 77.645 | 0 | 0 | 5 | 77.645 | 46.778 | 187 | 8747.486 | 192 | 8825.131 | 0 | 0 | 5 | 77.645 | 9.935 | 111 | 1102.785 | 116 | 1180.43 | 111 classrooms approved @9.9350
23.05 | ACR in lieu of upgraded Upper Primary School | 119 | 443.624 | 53 | 193.5 | 44.54% | 43.62% | 66 | 250.124 | 0 | 0 | 66 | 250.124 | 8.678 | 0 | 0 | 66 | 250.124 | 0 | 0 | 66 | 250.124 | 0 | 0 | 0 | 66 | 250.124 | Recommended as proposed
23.06 | Dilapidated Building (Pry) | 1 | 7.146 | 1 | 7.146 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 8.678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23.07 | Additional Class Room (Rural) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.08 | Additional Class Room (Urban) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.09 | Additional Class Room (Hill Area) | 213 | 1134.953 | 144 | 685.41 | 67.61% | 60.39% | 69 | 449.543 | 0 | 0 | 69 | 449.543 | 8.678 | 0 | 0 | 69 | 449.543 | 0 | 0 | 69 | 449.543 | 0 | 0 | 0 | 69 | 449.543 | Recommended as proposed
23.1 | Additional Class Room (Plain Area) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.11 | Additional Class Room (In lieu for PS sanctioned in previous year) | 1123 | 1661.186 | 349 | 690.82 | 31.08% | 41.59% | 774 | 970.366 | 0 | 0 | 774 | 970.366 |  | 0 | 0 | 774 | 970.366 | 0 | 0 | 774 | 970.366 |  | 0 | 0 | 774 | 970.366 | Recommended as proposed
23.12 | Boys Toilet | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23.13 | Separate Girls Toilet | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23.14 | CWSN Friendly Toilets | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.15 | Drinking Water Facility | 180 | 20.6326 | 1 | 0 | 0.5556% |  | 179 | 20.6326 | 0 | 0 | 179 | 20.6326 | 0.445 | 0 | 0 | 179 | 20.6326 | 0 | 0 | 179 | 20.6326 | 0 | 0 | 0 | 179 | 20.6326 | Recommended as proposed
23.16 | Boundary Wall | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.17 | Electrification | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.18 | Office-cum-store-cum-Head Teacher's room (Primary) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.19 | Office-cum-store-cum-Head Teacher's room (Upper Primary) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.2 | Boring and Handpump | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23.21 | Ramps with Handrails | 563 | 89.645 | 315 | 40.862 | 55.95% | 45.58% | 248 | 48.783 | 0 | 0 | 248 | 48.783 | 0.276 | 0 | 0 | 248 | 48.783 | 0 | 0 | 248 | 48.783 | 0 | 0 | 0 | 248 | 48.783 | Recommended as proposed
23.22 | Handrails in existing ramps | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.23 | Furniture for Govt. UPS (per child) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.24 | Major Repairs for Primary School | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | 16 | 4 | 16 | 0 | 0 | 0 | 0 |  | 4 | 16 | 4 | 16 | Recommended as proposed
23.25 | Major Repairs for Upper Primary School | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 24 | 6 | 24 | 0 | 0 | 0 | 0 |  | 6 | 24 | 6 | 24 | Recommended as proposed
23.26 | Residential Schools/hostels for specific category of children | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Construction of Building including boundary wall, Water and sanitation facilities, electric installation, kitchen shed | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (b) Construction of residential hostel | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 145.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (c) Refurbishing unused old buildings | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (d) Teacher staff room with toilet | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23.27 | Others (Difference of Civil Works sanctioned in previous year, SIEMAT, spillover etc.) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total ( Infra-Structure) | 2712 | 8137.1745 | 1008 | 3226.578 | 37.17% | 39.65% | 1721 | 4910.5965 | 0 | 0 | 1721 | 4910.5965 |  | 372 | 14661.881 | 2097 | 19572.4775 | 0 | 0 | 1721 | 4910.5965 |  | 212 | 3936.861 | 1933 | 8847.4575
VII | PROJECT MANAGEMENT COST | 0 |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
24 | Management | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
24.01 | Management up to 3.5% | 0 | [7 empty] | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Project Management and MIS | 0 | 496.4 | 0 | 422.45 |  | 85.1% | 0 | 73.95 | 0 | 0 | 0 | 0 |  | 0 | 880 | 0 | 880 | 0 | 0 | 0 | 0 |  | 0 | 787.35 | 0 | 787.35
| (b) Training of Educational Administrators | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (c) School Mapping and Social Mapping | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total | 0 | 496.4 | 0 | 422.45 |  | 85.1% | 0 | 73.95 | 0 | 0 | 0 | 0 | 0 | 0 | 880 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 787.35 | 0 | 787.35
24.02 | Learning Enhancement Programme (LEP) only for Large Scale Integrated Programmes for Quality Improvement (up to 2%) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| (a) Class I & II | 0 | 130.83 | 0 | 0 |  |  | 0 | 130.83 | 0 | 0 | 0 | 0 |  | 0 | 135 | 0 | 135 | 0 | 0 | 0 | 0 |  | 0 | 135 | 0 | 135
| (b) Class III to V | 0 | 130.83 | 0 | 0 |  |  | 0 | 130.83 | 0 | 0 | 0 | 0 |  | 0 | 135 | 0 | 135 | 0 | 0 | 0 | 0 |  | 0 | 135 | 0 | 135
| (c) Class VI to VIII | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 565 | 0 | 565 | 0 | 0 | 0 | 0 |  | 0 | 385 | 0 | 385
24.03 | Community Mobilization activities (up to 0.5%) | 0 | 103.6 | 0 | 62.04 |  | 59.88% | 0 | 41.56 | 0 | 0 | 0 | 0 |  | 0 | 181.25 | 0 | 182.8 | 0 | 0 | 0 | 0 |  | 0 | 141.99 | 0 | 141.99
| Sub Total | 0 | 365.26 | 0 | 62.04 |  | 16.99% | 0 | 303.22 | 0 | 0 | 0 | 0 |  | 0 | 1016.25 | 0 | 1017.8 | 0 | 0 | 0 | 0 |  | 0 | 796.99 | 0 | 796.99
| Total of SSA (District) | 515664 | 26743.5317 | 504617 | 15179.3431 | 97.86% | 56.76% | 13935 | 11564.1886 | 0 | 0 | 4910 | 10164.7621 | 0 | 471590 | 39137.6157 | 473315 | 49302.3778 | 0 | 0 | 4910 | 10164.7621 | 0 | 448516 | 24655.7976 | 453426 | 34820.5597
25 | STATE COMPONENT | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
25.01 | Management & MIS | 0 | 254.02 | 0 | 245.93 |  | 96.82% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 549 | 0 | 549 | 0 | 0 | 0 | 0 |  | 0 | 549 | 0 | 549 | Recommended as appraised
25.02 | REMS | 3881 | 56.03 | 0 | 54 |  | 96.38% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160.89 | 0 | 160.89 | 0 | 0 | 0 | 0 |  | 0 | 58.21 | 0 | 58.21 | Recommended as appraised
| Sub Total | 3881 | 310.05 | 0 | 299.93 |  | 96.74% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709.89 | 0 | 709.89 | 0 | 0 | 0 | 0 | 0 | 0 | 607.21 | 0 | 607.21
| STATE SSA TOTAL | 519545 | 27053.5817 | 504617 | 15479.2731 | 97.13% | 57.22% | 13935 | 11564.1886 | 0 | 0 | 4910 | 10164.7621 | 0 | 471590 | 39847.5057 | 473315 | 50012.2678 | 0 | 0 | 4910 | 10164.7621 | 0 | 448516 | 25263.0076 | 453426 | 35427.7697
26 | KGBV Financial Provision (give separate costing sheets for different Models) | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Non-recurring (one time grant) | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.01 | Construction of Building (New) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.02 | Construction of Building KGBV sanctioned earlier | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.03 | Boundary Wall | 11 | 98.1467 | 9 | 78.6106 | 81.82% | 80.09% | 2 | 19.5361 | 0 | 0 | 2 | 19.5361 | 15.97 | 0 | 0 | 2 | 19.5361 | 0 | 0 | 2 | 19.5361 |  | 0 | 0 | 2 | 19.5361 | Recommended as proposed
26.04 | Boring/Hanpump | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.05 | Electricity/water charges | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.06 | Furniture / Equipment (including kitchen equipment) | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 21 | 7 | 21 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Not recommended
26.07 | TLM and equipment including library books | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.08 | Bedding | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26.09 | Replacement of bedding (once in 3 years) | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Sub Total Non-recurring | 11 | 98.1467 | 9 | 78.6106 | 81.82% | 80.09% | 2 | 19.5361 | 0 | 0 | 2 | 19.5361 |  | 0 | 21 | 0 | 40.5361 | 0 | 0 | 2 | 19.5361 |  | 0 | 0 | 2 | 19.5361
| Recurring | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.1 | Maintenance @ Rs.1,500/- per girl Per month | 11 | 198 | 11 | 198 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 11 | 198 | 11 | 198 | 0 | 0 | 0 | 0 | 18 | 11 | 198 | 11 | 198 | Recommended as proposed
26.11 | Stipend @ Rs.100/- per girl per month | 11 | 13.2 | 11 | 13.2 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | Recommended as proposed
26.12 | Supplementary TLM, Stationery and other educational material @Rs.1,000/- per Girl per annum | 11 | 11 | 11 | 9 | 100% | 81.82% | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | Recommended as proposed
26.13 | Salaries | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
(a) | 1 Warden @ Rs 25,000/- per month | 11 | 33 | 11 | 33 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 11 | 33 | 11 | 33 | 0 | 0 | 0 | 0 | 3 | 11 | 33 | 11 | 33 | Recommended as proposed
(b) | 1 head teacher @ Rs. 25,000/- per month in case the enrollment exceeds 100 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
(c) | 4 - 5 Full time teachers as per RTE norms @ Rs. 20,000/- per month per teacher | 11 | 105.6 | 11 | 105.6 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9.6 | 11 | 105.6 | 11 | 105.6 | 0 | 0 | 0 | 0 | 9.6 | 11 | 105.6 | 11 | 105.6 | Recommended as proposed
(d) | 2 Urdu Teachers (only for blocks with muslim population above 20% and select urban areas), if required @ Rs. 12,000/- per month per teacher | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
(e) | 3 part time teachers @ Rs. 5,000/- per month per teacher | 11 | 19.8 | 11 | 19.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 11 | 19.8 | 11 | 19.8 | 0 | 0 | 0 | 0 | 1.8 | 11 | 19.8 | 11 | 19.8 | Recommended as proposed
(f) | 1 Full time Accountant @ Rs. 10,000/- per month | 11 | 13.2 | 11 | 13.2 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | Recommended as proposed
(g) | 2 Support Staff – (Accountant/ Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | 11 | 13.2 | 11 | 13.2 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | 0 | 0 | 0 | 0 | 1.2 | 11 | 13.2 | 11 | 13.2 | Recommended as proposed
(h) | 1 Head cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | 11 | 19.8 | 11 | 19.8 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 11 | 19.8 | 11 | 19.8 | 0 | 0 | 0 | 0 | 1.8 | 11 | 19.8 | 11 | 19.8 | Recommended as proposed
26.14 | Specific skill training @ Rs.1,000/- per girl per annum | 11 | 11 | 11 | 11 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | Recommended as proposed
26.15 | Electricity / water charges @Rs.1,000/- per girl per annum | 11 | 11 | 11 | 11 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | Recommended as proposed
26.16 | Medical care/contingencies @ Rs.1,250/- per girl per annum | 11 | 11 | 11 | 11 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 1 | 11 | 11 | 11 | 11 | Recommended as proposed
26.17 | Maintenance @ Rs.750/- per girl per annum | 11 | 8.25 | 11 | 8.25 | 100% | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 11 | 8.25 | 11 | 8.25 | 0 | 0 | 0 | 0 | 0.75 | 11 | 8.25 | 11 | 8.25 | Recommended as proposed
26.18 | Miscellaneous @ Rs.750/- per girl per annum | 11 | 8.25 | 11 | 7.5 | 100% | 90.91% | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 11 | 8.25 | 11 | 8.25 | 0 | 0 | 0 | 0 | 0.75 | 11 | 8.25 | 11 | 8.25 | Recommended as proposed
26.19 | Preparatory camps @ Rs.200/- per girl per annum | 11 | 2.2 | 11 | 2 | 100% | 90.91% | 0 | 0.2 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | Recommended as proposed
26.2 | P.T.A / school functions @ Rs.200/- per girl per annum | 11 | 2.2 | 11 | 2 | 100% | 90.91% | 0 | 0.2 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | Recommended as proposed
26.21 | Provision of Rent @ Rs. 6,000/- per girl per annum | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
26.22 | Capacity Building @ Rs.500/- per girl per annum | 11 | 5.5 | 11 | 5.25 | 100% | 95.45% | 0 | 0.25 | 0 | 0 | 0 | 0 | 0.5 | 11 | 5.5 | 11 | 5.5 | 0 | 0 | 0 | 0 | 0.5 | 11 | 5.5 | 11 | 5.5 | Recommended as proposed
26.23 | Physical / Self Defence training @ Rs. 200/- per girl per annum. | 11 | 2.2 | 11 | 2.1 | 100% | 95.45% | 0 | 0.1 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | 0 | 0 | 0 | 0 | 0.2 | 11 | 2.2 | 11 | 2.2 | Recommended as proposed
| Sub Total | 11 | 488.4 | 11 | 484.9 | 100% | 99.28% | 0 | 3.5 | 0 | 0 | 0 | 0 |  | 11 | 488.4 | 11 | 488.4 | 0 | 0 | 0 | 0 |  | 11 | 488.4 | 11 | 488.4
| Total (KGBV) | 11 | 586.5467 | 20 | 563.5106 | 181.8% | 96.07% | 2 | 23.0361 | 0 | 0 | 2 | 19.5361 | 0 | 11 | 509.4 | 11 | 528.9361 | 0 | 0 | 2 | 19.5361 | 0 | 11 | 488.4 | 13 | 507.9361
| Grand Total (SSA & KGBV) | 519556 | 27640.1284 | 504637 | 16042.7837 | 97.13% | 58.04% | 13937 | 11587.2247 | 0 | 0 | 4912 | 10184.2982 | 0 | 471601 | 40356.9057 | 473326 | 50541.2039 | 0 | 0 | 4912 | 10184.2982 | 0 | 448527 | 25751.4076 | 453439 | 35935.7058